## Migration
Resource Name | Project Name | Task Name | Detail Description | Daily Update (Date Wise) | Start Date | End Date | Status (Open/On hold/Completed/WIP)
Mane Gangadhar | TEO | Supporting to TEO Hypercare |  |  | 2026-01-01 | 2026-01-01
Himanshu Jain | TEO | Supporting to TEO Hypercare | Validating & Fixing issues for NX assemblies having issues with transforation matrix and constraints | (12/02/26)- Non-updated assmeblies validated and list prepared for the one's that are not opening without update. POC on QA paused due to priority PROD issue (04/03/26)- Resumed activity After BVRform and NX prod tickets resolution, Downloaded physcial files locally on at14 machine and tried opening assemblies in Local NX(report comparing with PROD prepared) (06/03/26)- Initial POC(locally generated CLONE file from physical files) on QA falied, Further POC ongoing (09/03/26)- POC completed for one ID(2 revisions) on QA. Remaining 17 assemblies are also being fixed in QA first. Once successful the same will be updated on Prod (20/03/26)- Update for all 19 assemblies completed on QA (27/03/26)- As discussed BOMLines from QA DB extracted for Prod loading instead of running UG_CLONE on Prod (28/03/26- but this isn't working correctly as some BOMLines notes are showing empty in extracted Table) | 2026-02-02 |  | WIP
Himanshu Jain | TEO | BVRSyncInfo Form ownerhip Update Script | To find Datasets(ownership updated as part of TEO but secondary object (Forms)ownership not updated via ITK, giving issue in revise) | (19/02/26)-POC complete and update done for samples but QA AWC is giving issues. same samples tested on Dev and Prod(checking for more IDs before running on PROD) (23/02/26)- Awaiting On-site team approval for bulk PROD run (24/02/26)- On site team has requested for affected sample IDs which they will verify before update and then once after we update those(shared report) (25/02/26)- Confirmation recived from on-site team regarding shared IDs, running update for these(once updated IDs validated will run update for bulk) | 2026-02-13 | 2026-03-02 | Completed
Himanshu Jain | TEO | Tickets raised for physical files missing under named_ref | Due to multiple spaces in File_Name, the SD_PATH update scipt has updated wrong sd_path for datasets leading to no named_ref size/no dataset migrated in case of MNF | (20/02/26)-List of such cases extracted from PROD and validated, Reported ticked ID also fixed. Update for other affected(count-45) in process (23/02/26)- After valdiation around 22 of these 45 Dataset were found with issues and update for the same was complete by correcting sd_path in csv manually | 2026-02-20 | 2026-02-23 | Completed
Mane Gangadhar Deepak Suryawanshi | TEO | Supporting to TEO Hypercare | Currently Validating Catia Assembly on PROD env | Deepak: (4/3/26) - Checked the T4s Material transfer to SAP via TTT Admin Workflow validation from the SAP environment(QU1) from Teamcenter QA. Deepak: (5/3/26) - Supported in the User Ticket resolution activity(Incident no: INC0283884). | 2026-02-02 | 2026-02-06 | Completed
Piyush Hedaoo | Phinia G3.2 | Working on reports | Working on CBA Reports and other scenarios |  | 2026-02-02 |  | completed
Vilas Baviskar | Phinia G3.2 | Supporting On CBA Alignement Reports | Working on CBA Reports and other scenarios | Cloning the Production Tables to staging | 2026-02-02 | 2026-02-03 | Completed
Vilas Baviskar | Phinia G3.2 | Working on CBA alignment reports | Working on CBA alignment reports |  | 2026-02-03 | 2026-02-03 | Completed
Vilas Baviskar | Phinia G3.2 | PPAP Data Report from GES | Identifying the PPAP data in GES database and Preparing report |  | 2026-02-04 | 2026-02-06 | Completed
Mane Gangadhar | TEO | Working on TEO CR Document and Timeline activity | Working on TEO CR Document and Timeline activity. Working on Catia Failed assemblies for TEO Project. |  | 2026-02-09
Vilas Baviskar | Phinia G3.2 | new Reports asked by DAVE | preparing reports for multiple scenario's as asked by Dave | New reports has now been shared with Dave. Waiting for his reply | 2026-02-17 | 2026-02-23 | Completed
Piyush Hedaoo | Phinia G3.2 | new Reports asked by DAVE | preparing reports for multiple scenario's as asked by Dave |  | 2026-02-17 | 2026-02-19 | WIP
Vilas Baviskar | Phinia G3.2 | Analysing ECAD Data for MCAD ECAD Collaboration | Analysing ECAD Data for MCAD ECAD Collaboration |  | 2026-02-17 |  | WIP
Gangadhar | TEO | Migration of newly secured Data from SAP PLM which wasn't part of original scope | 1.Data Extraction From SAP to Text file 2.Physical file extraction 3.Import extracted data to staging database 4.Extraction and Transformation on imported data 5.Tiff to PDF convert 6.Data loading in Teamcenter (QA,PROD) 7.Data validation on QA env | 23Feb26-Data extraction is from SAP for 79 MM and compare with staging database and found 30 material and shared report with customer. 05Mar26 - Preparing CR enhancement related document. | 2026-02-23 |  | WIP
Piyush Hedaoo | DANA PMA & SYMBOTIC | Preparing New reports related to DANA PMA
Pranay | DANA PMA | Completed
Vilas Baviskar | Phinia G3.2 | Prepare Different Scenarios for CBA Alignment | For CBA Alignment we need to prepare AS-IS and TO BE scenario to get the approval from the SME's | 05 March- Preparing Slides for CBA Alignment scenarios Deepak (05/03/26) - Supported on preparation of Slides for CBA Alignment scenarios | 2026-03-05 |  | WIP
Himanshu Jain | TEO | NX assembly/Drawing issue | NX assembly for latest revision wasn't opening as BVR itself wasn't available in PROD, had to reimport and re-release the same | (04/03/26)- Assembly has been fixed but petra(client) has some issue with drawing related to assembly (have pinged her to connect for clarity) | 2026-03-03 | 2026-03-04 | Completed
Himanshu Jain | TEO | Item Revisions with Release Status not updated | Some older revisions were showing as WIP in target whereas they were released earlier(this happened due to status update being skipped due to older lsd than UG_CLONE run) | (04/03/26)- ID shared by client has been fixed, check and update for other affected items is on going | 2026-03-04 | 2026-03-05 | Completed
Unnat Mishra | DANA PMA | Completed. | DANA PMA completed then DANA Proposal with Rahul Bharadwaj completed.
Himanshu Jain | TEO | NX datasets have physical files missing and some datasets have release flag but no status | Some NX datasets have issue in Named_ref and are imported as empty dataset(having only form and no physical file) and there was one reported ID for which Dataset shows Release staus flag but there is no release status | (10/03/26)- Had Call with on-site team to discuss the issues, physical file missing being the priority(as release status flag was for only one ID). RCA for this is ongoing to check input files as multiple machines were involved during PROD loading (11/03/26)- Reported ID has been fixed and analysis for such affected IDs is running | 2026-03-10 | 2026-03-12 | Completed
Vilas Baviskar | Phinia G3.2 | Extraction and Transformation of Data | We need to Realign the Relation for the CBA alignment | 09/04/26 ---Working on the Extraction and Transformation of the Data for Project Phinia G3.2 16/04/26--- Testing the Loading utility and will start loading in QA Environment 20-04-2026-- Dave Requested new report, So working on it, As well as Will start loading in QA environment today. | 2026-04-08 |  | WIP
Pranay Devarapalli | Phinia G3.2 | Glenn Moulder Requirement(Converting DR to CI) | Converted 17 IDs from DR to CI in QA | 16/04/26 - Will proceed convertion on PROD once Glenn Moulder check and confirm on QA 20/04/26 - Validation done for 17Ids in QA; Will be sharing the same to Glienn Moulder for UAT | 2026-04-13 |  | WIP
Piyush Hedaoo | Phinia G3.2 | Robocopy | Robocopy in progress for Deisgn objects | 16/04/26 - Robocopy in progress 20/06/26 - Robocopy in progress (Expected to complete in 2-3 days) | 2026-04-15 |  | WIP

## Integration
Resource Name | Project Name | Task Name | Detail Description | Daily Update (Date Wise) | Start Date | End Date | Status (Open/On hold/Completed/WIP)
Bhau Shelar/Shubham D | Borgwarner(T4S) | Delta BOM changes. | Transfer only updated changes to SAP. | 24/02/2026-Development is completed. 25/02/2026-Handover to validation team to validate all the use case. 02/03/2024- Delta BOM Transfer Demo completed to key user. 04/03/2026-Resoved all the validation error and revalidated. 05/03/2026 - Ready to deploy on QA server. 09/032026- waiting for Ram confirmation to deploy on QA. 16/03/2026-After discussing with Ram, we planned to deploy the changes on the QA environment. Once the deployment is complete, we need to validate all use cases in QA. After validation, we will schedule a demo with Paulina tomorrow. 23/03/2026- The demo is complete. They suggested a new use case. We are checking that if it is feasible or not. Also found one issue on related to BOM transfer and I am checking that. 27/03/2026--The follow up demo has been completed, and the customer has proposed an additional requirement. If any SAP component Find Number differs from the corresponding Find Number in Teamcenter (TC), the BOM should not be transferred to SAP. Instead, the system should block the transfer and display an error message for that BOM transfer. 30/03/2026--Development has been completed. If an SAP component is placed at a different position (Find Number) in Teamcenter (TC), the system will display an error and block the BOM transfer to SAP. The solution will be provided to the validation team for testing today. 03/04/2026-- We have planned follow up customer demo on Wednesday. 10/04/2026- We have done customer demo on 10 april. 14/04/2026- We have done demo for china and singapore users. 15/04/2026- We planed demo for Reynosa and SPL team. 17/04/2026--UAT has been completed for the Blonie China and Singapore plant user. Suggested one change for delete any BOM line should be check component is same otherwise show error for transfer. 20/04/2026--UAT has been completed for Viana user. Also completed delete component usecase UAT with Blonie users. | 2026-02-02 |  | WIP
subham mohanty | PHINIA | Data Lake | Development of Java Runnable Batch Application to extract recently modified Item Revisions from Teamcenter Oracle DB based on time‑based delta logic | -> 06/03/2026-: Requirement analysis completed for Latest Item Revision extraction from Teamcenter database using time‑based delta logic. -> 09/03/2026-: Developed REST based approach extracting modified Item Revisions using Oracle SQL query. -> 10/03/2026-: Developed standalone Java Runnable JAR for extracting modified Item Revisions using Oracle SQL query. -> 23/03/2026-: Removed the earlier time‑frame–based logic that relied on the scheduler’s latest run time to post data every 30 minutes. ->24/03/2026 –: Added a 1‑day time frame filter to the query and successfully extracted data into the MySQL table. Logic verified and working correctly. ->30/03/2026 –: Implemented dynamic delta-based extraction using last_run_time control table to fetch only newly modified Item Revisions from Teamcenter Oracle DB. Developed and deployed standalone Java Runnable JAR with batch script for automated execution. Configured scheduler to run every 30 minutes. Added conditional logic to update last_run_time only when new data is processed, ensuring no data loss. End-to-end flow tested successfully and validated with logs. | 2026-03-06 | 2026-03-31 | completed
Bhau Shelar/Shubham D | Borgwarner(T4S) | TTT T4S issue (MM) | There is an MM creation issue for software parts. An issue was received where the part number for a software part is transferring an incorrect value. | 16/03/2026--I have tested this case, but I was not able to replicate the issue in the QA environment. I am continuing to investigate the issue. 23/03/2026- Investigating this issue but not able to found out the issue. Still I am working on this issue. 30/03/2026--Other than Prototype status software parts are transferring to SAP. Still I am working on investigate this issue.
Bhau Shelar/Shubham D | Borgwarner(T4S) | TTT T4S issue (BOM) | There is an issue with BOM transfer. The reported problem is that PV and DV BOM lines are not being transferred to SAP. | 16/03/2026- The primary analysis indicates that we have set the PDS latest in work revision rule by default through preferences. However, for TTT, we are setting the revision rule to Precise only using a workflow argument, and this is not fetching the correct BOM lines. 18/03/2026- Found issue in workflow not added revision rule argument in other workflows. 23/03/2026- issue fixed in QA and user is validating this issue. Once confirmed we will push this changes in PROD.

## Training
Resource Name | Training Module | Task Name | Detail Description | Daily Update (Date Wise) | Start Date | End Date
Nikhil,Pranay,Vipin,Omkar | Admin | Installation of TC Foundation | Installed and configured Teamcenter Foundation services |  | 2026-01-23 | 2026-01-23
Nikhil,Pranay,Vipin,Omkar | Admin | Installation of Server side features on TC Environment | Installed required Teamcenter server-side features |  | 2026-01-27 | 2026-01-27 |  | Location of Training Documents: https://tatatechnologies.sharepoint.com/:f:/r/sites/BorgWarnerProject/Shared%20Documents/Delivery/Source_Code_Repository/KT_Sessions?csf=1&web=1&e=1qokYq
Nikhil,Pranay,Vipin,Omkar | Admin | Installtion of 2T Client | Installed and validated Teamcenter Rich Client (2-Tier) |  | 2026-01-27 | 2026-01-27
Nikhil,Pranay,Vipin,Omkar | Admin | Installation of Server Manager | Configured Server Manager |  | 2026-01-28 | 2026-01-28
Nikhil,Pranay,Vipin,Omkar | Admin | Installation of Web Tier | Installed and configured Teamcenter Web Tier |  | 2026-01-28 | 2026-01-28
Nikhil,Pranay,Vipin,Omkar | Admin | Installation of AWC | Deployed Active Workspace Client application |  | 2026-01-28 | 2026-01-28
Nikhil,Pranay,Vipin,Omkar | Admin | Deployment of Custom Data Model | BMIDE client Installation and deploy BMIDE Template Ttl (Project:t9ttl) |  | 2026-01-30 | 2026-01-30
Nikhil,Pranay,Vipin,Omkar | Admin | Installation of Active Workspace Indexing | Indexer server Installation |  | 2026-01-30 | 2026-01-30
Nikhil,Pranay,Vipin,Omkar | Admin | Installation of Dispatcher | Dispather server and Dispatcher Client Installation |  | 2026-01-30 | 2026-01-30
Nikhil,Pranay,Vipin,Omkar | Admin | Configuration of SSO | Integrated Single Sign-On authentication |  | 2026-01-21 | 2026-01-22
Nikhil |  | Reapply Patch 05 On HNJPHINIASRV01 Machine | Reapply Patch 05 On HNJPHINIASRV01 Machine |  | 2026-02-03 | 2026-02-03
Somnath | BMIDE | Training on BMIDE | Provided detail level training sessions |  | 2026-02-04 | 2026-02-09
Nikhil,Pranay | BMIDE Assignments_1 | BMIDE Use case template development | Create BMIDE Projects and custom business objects and properties and deploy latest BMIDE templates into Training Teamcenter Env |  | 2026-02-05 | 2026-02-05
Vipin | BMIDE Assignments_2 | BMIDE Use case template development | BMIDE template update with BMIDE assignments and deploy latest BMIDE templates into Training Teamcenter Env |  | 2026-02-10 | 2026-02-10
Rushikesh | AWC Stylesheet, Preference | AWC Configuration Training | AWC Stylesheet and Preference creation | 10 Feb:- AWC Stylesheet and Preference creation Completed. | 2026-02-10 | 2/102026 | Completed
Ashutosh | Query Builder and Organization | AWC Configuration Training | Query Builder and Organization | Query Builder and Organization | 2026-02-11 | 2026-02-11 | Completed

## Implementation
Resource Name | Project Name | Task Name | Detail Description | Daily Update (Date Wise) | Start Date | End Date | Status (Open/On hold/Completed/WIP)
Kuldeep Bhise | Syberjet | Development of Workflow | Workflow with Custom and ootb handler | 10 Feb:Configured the workflow, however JT to CGR not working 11 Feb:Release status stamping not working correctly 13 Feb:Prepared and shared test cases to customer 04 March: Deliverd workflow and working correctly, however customer raised concern on NX reference set name = Item Id. 03/11/2026 - out of scope(sandeep is looking in it) | 2026-02-03 |  | Completed
Kuldeep Bhise/Ashutosh | QMS | Development of Quality management | Installed Quality management | Working on FMEA and Control Plan, in Teamcenter Quality. There are 1 issues in QMS, Raised IR for that. 02/26/2026 - Working on formsheet, to add columns and chage the Logo. 03/04/2026 - Able to change he LOGO and added the new column in formsheet. 03/04/2026 - No further update on PMI for 2D drawing issue. 03/10/2026 - Call is scheduled in 03/17/2026 with BCT Team, to understand the our Requirements. 03/10/2026 - Checking the diffrent way to convert the PDF into DXF file. 03/12/2026 - Mail is sent to Milind and Murugan about BCT LIcense. 03/25/2026 - Connected with BCT Team, got the input about about Licencse code which is required for BCT from Siemens. Alredy Mail is sent to Murugan, need to raise a request for demo license 04/01/2026 - Unfortunately the product BCT900921 is not available for demo licenses. You must proceed with a zero-dollar commercial order in a "non-demo" install. So we requested Murugan for zero-dollar licence 04/10/26 on hold 22/04/2026:Murugan shared some information.Need to check | 2026-02-02 |  | Hold
Ashutosh Shimpi\Rushikesh\Varsha | Epiroc | Epiroc | AWC Configuration,MBOM, BOP, CM | 02/26/2026 - Had a meeting with Bhavtesh and Team, from Monday the work is going to start on BOP, Chnage Management,CBA 03/04/2026 - Daily meeting is schedule with EPIROC Internal Team, work Distribution is in progress. 03/11/2026 - Meeting is scheduled with EPIROC Team about the Agile Methodology overview and Developemen activities about Build, deployement. 03/17/2026 - Got the access of EPIROC Teams and Outlook, VDI access is still Pending. 03/25/2026 - Stylesheet Configuration is completed for 3 Items, working on Tile Configuration and UI changes. and Parallary checking the custom RAC Command. 04/01/2026 - Working on Change Management Workflow, Tile Configuration, Document Management etc. and working on Smart Git Setup. 04/08/2026- Stylesheet creation for Documents and its type. There are around 11 types of Document. 04/10/2026- EBOM Objects stylesheet creation, BMIDE analysis(GRM rule, Display rule). Arranged Internal Demo session yesterday for AWC configuration deployments on personal VM. 04/15/2026 - Working on Product Configurator, CAD BOM E BOM, Document Management, and Configuration, Column Configuration 04/22/2026 - Working on Product Configurator, 17 Test cases Completed out of 24, in Next week Internal Demo will be scheduled. 04/22/2026- Working on Document Management. 11 types of Document object. Stylesheet creation done for all objects. Working on SUCs. | 2026-02-26 |  | WIP
Somnath | BW | QA BMIDE and DLL Deployment | QA ENV Deployment |  | 2026-02-03 | 2026-02-03 | Completed
Shashi | BW | QA BMIDE package preparation | Done on QA and Dev Following points where deployed on Prod -LOV update :BWR3_Programs on Morse CR with 5 values OWC,Controls,BSL,BRL,BSSP -Display Name change for BWR3_MorseCR to DMS CR,BWR3_MorseCRRevision to DMS CR Revision,BWR3_MorseCI to DMS CI,BWR3_MorseCIRevision to DMS CI Revision -DLL update :TTT_Handlers.dll -Part Numbering Naming rule update for DT_RefItem -Display Rule change for BWR3_BWDocument -Property Constant update for DT_Item,DT_RefItem,DT_MFG,BW Software,BW Material,BW ChartDWG,BW Document -Solution folder all items are not visible in tree view - more than 50 objects. | 30Jan: Completed | 2026-01-30 | 2026-01-30 | Completed
Nikhil | KDrive Support | 4T client Configuration | 4T client Configuration | 05 Feb:Completed | 2026-05-02 | 2026-05-02 | Completed
Shashi & Somnath | BW | Prod BMIDE package preparation | Following points where deployed on Prod -LOV update :BWR3_Programs on Morse CR with 5 values OWC,Controls,BSL,BRL,BSSP -Display Name change for BWR3_MorseCR to DMS CR,BWR3_MorseCRRevision to DMS CR Revision,BWR3_MorseCI to DMS CI,BWR3_MorseCIRevision to DMS CI Revision -DLL update :TTT_Handlers.dll -Part Numbering Naming rule update for DT_RefItem -Display Rule change for BWR3_BWDocument -Property Constant update for DT_Item,DT_RefItem,DT_MFG,BW Software,BW Material,BW ChartDWG,BW Document -Solution folder all items are not visible in tree view - more than 50 objects. | 30Jan: Completed | 2026-02-07 | 2026-02-07 | Completed
Rushikesh Gadkar | Training | AWC Configuration Training | AWC Stylesheet and Preference creation | Stylesheet and Preference | 2026-02-10 | 2026-02-10 | Completed
Ashutosh Shimpi | Training | AWC Configuration Training | Meeting is scheduled to give Training on AWC Configuration/Application. | Query Builder and Oraganization | 2026-02-11 | 2026-02-11 | Completed
Harshvardhan | BW |  | 02-11-2026 :Working on Export Issue ACL change for TEO 02-18-2026: Working on stylesheet issues in BW |  |  |  | Completed
Shashi & Rushi | BW | Workflow modification for water marking issue | Previous object should get invalid status (presently doing) additionally the pdf under the object should be watermarked as invalid. | Workflow (custom handler) 20thFeb: we have modified the handler (added new relation for stamping IMAN_manifestation) ,validation is in progress 26_Feb2026: Validation of invalid stamping completed by Darshna and Pratik.Also asked user to test same use case on QA in hypercare call (26th Feb) 03Mar26: Need to check for other status. 09March26: Validation for other status completed by validation team | 2026-02-12 |  | Completed
Shashi & Harshvardhan | BW | Release status issue | When viewing attachments of a DT_Item the flag colors are the same for both PV and DV released items. The colors should be different. Also, when I open the DT_ref item using the open box icon the DV&PV flags are blue. If I open the same DT_ref item by clicking on it the same DV&PV item's flags are orange. the flag colors shouldn;t change depending on how the items are opened. | 20Feb: we need to discuss how to handle, as the real name for the flag contain "_" in bmide, 24Feb: Currently on hold. 4March:explore more 16March: Willl discuss with pasha and Run team 18March: Shashi will schedule call to discuss 20March: On Hold communicated to customer - workaround use table view | 2026-02-06 |  | Completed
Somnath & Nikhil | Phinia | BMIDE Deployment | New Attribute need to add on chnage objects and Naming rule need to deploy | 18_Feb: waiting for confimration from NM 25_Feb: Today got the confimration from NM, after 7.30 PM IST deployment need to plan, now preparing package 26_Feb: Deployment completed, DM Testing is in progress also DLL need to deploy on QA. Somnath - 4 March: Validation completed, UAT yet to be planned then we need to plan for prod Deployment. Somnath - 4 March: Customer Demo planned on 6 March. 03/11/2026 - QA- completed, Prod -Pending schedule on 03/15/2026. 18/03/2026 - Deployment in Production is rescheduled on Sunday 22/03/2026 | 2026-02-18 |  | Completed
Puneeth | Internal TTL | Mentor & EDM Licenses | Follow-up with Ram to procure the licenses for Mentor, EDM & Integration gateway List of licenses have been provided to Ram -(30/01/2026) meanwhile exploring into End-to-End Integration of Mentor, EDM & Teamcenter | 18_Feb: Following-up with Milind Joshi and Ram for procuring the Tools & Licenses 24_Feb: Got in touch with Sam Team (Tushar & Murugan) based on Milind suggestion over teams. Mail to be sent to team. 25_Feb: Mail sent to SAM team 27_Feb: No response yet to email. Reminder shall be sent. 02_Mar: Reminder sent 04_Mar: GTAC IR should be raised 11_Mar: GTAC IR to be shared with Murugan 11_Mar: GTAC raised asking the Product ID details 12_Mar: Connect with Ravi/ Ram for pricing book details 16_Mar: Follow-up with Ravi/Ram for availability 18_Mar: Puneeth will connect with Ravi/Ram as per their availability & discuss. 20_Mar: Received Bundle Information from GTAC & downloaded the bundle via excel 23_Mar: Went thru' the bundle for required Product ID & description 27_Mar: Mail sent to Murugan requesting the same with respective Product ID 30_Mar: Follow-up with Murugan 31_Mar: Seimens asked to raise a Patner support request 2_Apr: Unable to access the link shared by Seimens support team 6_Apr: Patner support request form filled with the help of Pavan,Pyati 8_Apr: Have requested the SAM team to check the availability of OrCAD Integration demo license 15_Apr : Puneeth will going to send reminder Email. 16_Apr: Reminder mail sent, Murugan replied no response from Siemens yet 17_Apr: Awaiting for the license key from Siemens 22_Apr: Puneeth is following with Murugan.Kuldeep is checking with Marelli team,as Integration with Orcad is already in place. | 2026-01-30 |  | WIP
Nikhil | Phinia | Provide detail flow diagram of FusionPLM Production to TTL DR Project team | Provide detail flow diagram of FusionPLM Production to TTL DR Project team | 19Feb:Complete | 2026-02-18 | 2026-02-19 | Completed
Shashi & Somnath | TEO | BMIDE Deployment (for DEV, QA, Prod ) | Upcoming deployment for item id and attaching the LOV for the Project ID Attribute on BW Software | 26 Feb: Today discussion with Andrew and team regrading the deployment. 02 March: Deployment needs to be planned with CR deployment. 18 March: Meeting scheduled today for discussion on BP 57 deployment on QA and Prod with Pasha and Run team 20 March: QA deployment completed on 24 March testing is in progress 27 March: Additional request reported which we deployed again in QA ENV next action is PROD Deployment plan on saturday 28th March 5PM IST 28 March: Deployment completed successfully on PROD | 2026-03-18 |  | Completed
Nikhil | Phinia | Prepare document for Applcation changes done in Phinia Production environement on 07 March2026 | Prepare document for Applcation changes done in Phinia Production environement on 07 March2026. These changes are done to make application DR ready | 3/10/2026[Nikhil]: Document completed | 2026-09-03 | 2026-10-03 | Completed
Kuldeep Bhise/Piyush | Symbotic | Questionnaire (Siemens, Generic, Pain areas) & Worksop preparation | Questions and Pain area preparation | 3 March: Prepared pain areas and shared 10 March: Prepared Siemens Questionaries 18 March: Workshops are scheduled from next week 27 March: Questionnaire is ready & currently it in use for ongoing workshop 10Apr: Call with Customer. 15 April : To Be process alredy completed, Waiting for bhavtesh review, Open point regarding Cost 22 April: As-Is & To-be Process documents has been shared. Cost & effort estimation documents will be shared. | 2026-03-03 |  | WIP
Puneeth & Gaurav | Phinia/SEM | ECAD Harmonization | Phinia and SEM Harmonization | 18_March: Initial internal dicussion with Ajay to understand Orcad. 20_March: Connected with customer requested to prepare questionaire and meeting is scheduled for 25th. 23_March: Internally connected with Ram and finalized prepared questionaires and sent to Customer. 25_March:Conducted a meeting with the customer and worked through the questionnaire, completing about 50%. 27_March:Reviewed and completed all questionnaires during the customer engagement 30_Mar: Had a meeting to understand the SEM Infra 2_Apr: Prepared PPT slides for Current AS-IS Landscape & Harmonized approaches 8_Apr: Had a discussion to understand the ECAD data in Windchill 10-Apr: Meeting scheduled by Ram with Xavier & Team 14_April: Had discussion with Ravi for future ECAD landscape compatibility 15_April: Exploring Cadence OrCAD Integration with Teamcenter 16_April: Working on Comparison of BOM Structure, Exploring the limitation/ Challenges & doubts from Ravi 22-April - Puneeth & Gaurav exploring ECAD Structures. | 2026-03-18 |  | WIP
Shashi | TEO | BMIDE Deployment (for DEV, QA, Prod ) | TEO CR implementation | 30 March: Phase 1 Implementation Progress – DEV Server We have initiated the first phase of implementation activities on the DEV environment, focusing on the following enhancements: A] Description attibute Enhancements (TTT CR & TTT DR Revision) - Introduction of a new custom attribute with 2048 string length. B] Field Expansion - Extension of the character attribute based on to 16 string length for DT_Item/DT_MfgItem. C] Product Family attribute - Adding of the TTT Product Family attribute within the TTT DR revision with required LOV. D] Addition of the bwr3_sync_prototype_to_sap attribute within the following LOV (bwr3_sync_prototype_to_sap) on TTT DR revision a. “No” (as default value) b. “PU1” c. “EP3” d. “both” 01 April : BMIDE Package is Ready for Deployement, today deployement is scheduled on Dev. 02April: Deployment Done on DEV. 11April: Deployment Done on QA | 2026-03-30 |  | Completed
Somnath & Nikhil | Phinia | QA Cloning | QA Cloning need to perform for DR | 4/6/2026: Waiting for SMEs confimration then we will start closning activity 10Apr: Testing going on. 10April: Cloning completed |  |  | Completed
shashi | TEO | Workflow | 1. "Part Number Generator WF - Prototype Sync In case Release Status ""Prototype"" is selected, the initiator will be asked to which SAP system (EP3 or PU1 or both) the sync should be applied" 2. Sync Prototype Release to SAP - Design Release workflow TTT_DR 3. Expansion of quick release Admin workflow - efficiently move more object types to approved status (today only BW Document) | 03-Apr-26: Workflow deployment done on DEV for all 3 points. First round of validation done. 10-Apr-26: Will send mail to validation team to validate on DEV. 12-Apr-26: will Deploy Workflow changes on QA. 16-Apr-26: Deployed all Workflow changes on QA. 17-Apr-26: Will send mail to validation team on QA for all workflows 20-Apr-26: Mail shared with validation team to validated sprint 1 workflow(REQ_CR26-01-006 - Quick release workflow access for global document admin role) on QA |  |  | WIP
shashi | TEO | Stylesheet | 1. Stylesheet update for OOTB attibute on TTT objects: ID Revision Release Status Name Last Modified User Description Owner Date Modified Type Date Released 2. Added 2 columns in reference section of attachment tab | 02-Apr-26: prepared the style sheet on DEV. 08-Apr-26: Deployed stylesheet changes on DEV. 10-Apr-26: Will Send mail to validation team to validate on DEV 12-Apr-26: Deployed stylesheet changes on QA. 16-Apr-26: Made changes in stylesheet and shared mail with validation team. 18-Apr-26: Validation Complete |  |  | Complete
Somnath/Pranay/Himanshu | VIPER_IP | Project Creation | New project and ACL creation | 21-April-26: Somnath - New project created 22-April-26 : Somnath -Latest ACL is created in QA Testing is in progress, QA deployment need to plan for condition and propagation rules. | 2026-04-21 |  | WIP
Nikhil | Phinia | Migration from LDAP to LDAPS | Right no

## Development
Resource Name | Project Name | Task Name | Detail Description | Daily Update (Date Wise) | Start Date | End Date | Status (Open/On hold/Completed/WIP)
Shubham Dukare | Phinia | BOM Excel Reports | Development of custom BOM Excel reports ( Phinia Reports Portal ) which will download the BOM report in excel format | 4) 04-03-26: Analyzing the rev rule issue reported by internal validation team 5) 06-03-26: It's not an issue, The issue is with sandbox server data sync 6) 10-03-26: Waiting for the demo to customer. 7) 19-03: Demo completed in pulse meeting. Deployed on QA env. 8) 25-03: Need to test the newly updated revision rules 9)27-03: Validation team is testing the newly updated revision rules 10)31-03: QA Validation of BOM Excel Reports has been completed successfully. We have asked Dave to validate the BOM Excel Report on Fusion PLM QA. Once he completes his validation then we can plan for PROD Deployment 11)08-04: Haven't received any feedback. Bhau has sent a reminder mail on 3rd April. 12) 14-04: Same status 13) 17-04: Somashekar is looking for the slowness issue of query execution in FusionPLM QA AWC. For the column configuration, we need to connect with Oliver. Dave agreed with the column configuration. Dave asked to connect with Oliver. 14)22-04: Had a discussion with Dave, Anthony & Alain yesterday. We need to update the code to add the new enhancements. | 2026-02-13 |  | WIP
Shubham Dukare | Phinia | Responsible Party Report | Development of the responsible party custom report which runs each hour and override the report file | 4) 04-03-26: working to add new attributes in report Need to schedule internal demo 5) 06-03: waiting for the result from internal validation team. Demo scheduled today with customer 6) 12-03: Excel columns have been updated as per the sheet shared by elina 7) 17-03: Elena & Dave agreed with the excel sheet columns 8) 19-03: Planned deployment on PROD by this weekend 9) 25-03: Will connect with NM and start the schedule job today 10)27-03: Deployed on prod utility server. Need to share the code location with NM 11)31-03: code location is shared with NM. Haven't received any issues till the time 12) 08-04: Task is completed | 2026-02-16 | 2026-03-11 | Completed.
Shubham Dukare | MBSE Lab | Custom SAP Integration | Have to transfer the BOM and CM to the SAP | 1) 04-03-26: BOM & CM Transfer was not working due to error in the SAP Application 2) 19-03: It's SAP Issue, SAP is not configured properly.Waiting for the Teamcenter start. Teamcenter services are unable to start properly. Khosla Shantanu will inform us once TC is ready. 3) 14-04: There is an error mentioning to enter an industry sector for the MM Transfer. We are working on it 4) 17-04: Bhau needs to look into
Shubham Dukare | SyberJet | Recompile code | Recompile the code for the new teamcenter version 2506 | Veeru sent mail to maarc to test the functionality 1) 20-02-26: Testing ongoing 2) 24-02-2026: Same Status. 3) 17-03-26: Same Status. | 2026-02-03 |  | Completed.
Krutika Jawase | TEO | TEO Reports | Report on DR, Maturity Shift for Approval - Create a report for TTT_DR and BW Maturity Shift objects, to improve the review and approval of the WFs being applied. The report should allow to view customer-specific attributes for a quicker review process. | 5/3/26:- Based on the team discussion, we have changed the approach of TTT DR report from the ITK custom report to the Summary report as per the requirement. Write post action for update TTT Product family attribute from DR to solution objects..(On DR there is no Product family attribute available…using description property for testing) Created report definition on QA env as well as Started working on ITK custom report code. 05/03/2026 : As per team discussion, change approch ITK custom report to Summary report as per the requirement.Create Summary report with property set and query.. 09/03/2026: Discuss TTT DR repoort with Gangadhar and need to changes report as per requirement. 24/03/26: As per the discussion with gangadhar , need to add some more attribute to generate report like creation date, owning user/ group and some attribute in DR Report 26/03/26: working on input field criteria field attribute, done with additional attribue add in DR report 3/04/26:- DR report 70% completed , maturity shift is 50% complete working on DR and maturity report on excel format. 7/04/26:- DR report & maturity report is completed 14/04/26:- validation is done need some issue to be fixed from my side |  |  | complete
Krutika Jawase | TEO | TEO Reports | TTT CR report | CR reports some value is not getting populated properly |  |  | WIP
Krutika | TEO | User DB | Create Logs for user db portal. After editing user information in edit page approver is not getting assign properly one approver user is not getting email from user | 24/03/26:- Done with Log creation for user db 26/03/26:- woring on issue , editing user information approver is not getting assign properly 1/04/26 :- issue is fixed testing is done and war is deployed on prod 20/04/26:- approver is not getting email request from user |  |  | WIP
Krutika Jawase | Phinia | Dx-assembly | Dx-assembly release status issue, fixing | 6/03/2026:- DR connection changes done 10/03/2026:- In some senrio some mix revision id query was failing in certain cases issue is fixed. 11/03/2026:- Testing and latest package need to release. will share latest package to junaid to validate. 12/03/2026:- All issue fixed from our side and also testing is done . 13/03/2026:- After conformation PROD package will share with Junaid and team , package has submitted |  |  | Completed.
subham mohanty | TEO | TEO REPORTS(EBOM/DBOM) | During TEO migration project new attributes were introduced by TTT and existing attributes were mapped from SAP PLM. These attributes are also relevant for getting displayed in a BOM (EBOM / DBOM) view in Teamcenter. Therefore, the TTT business is requesting to make the following attributes available in the “Available Columns” section, when an item is opened in the content view and after the gear icon is clicked and “Arrange” is selected | 2/4/26->Right now all the data is coming according to the object type, but the sample Excel report is still blank. Work on that excel report is still pending. 5/4/26->I have tested everything from my side and all the values are also coming correctly for HTML reports. I had a few doubts related to Excel report generation. 6/4/26->tested everything from my side and all the values are also coming correctly. | 2026-03-30 | 2026-04-06 | Completed.
subham mohanty | TEO | TEO REPORTS(Enhancements Requirements) | BOM (EBOM / DBOM) | 7/4/26-> I added the real name attribute to the propertySet, created Excel and HTML report pages, removed extra <div> elements such as the search criteria template from the report and added CSS to the HTML for TTT_DR Revision,TTT_CR Revision. 8/4/26-> I fixed the broken column in the Excel page. updated the CSS properties in both the HTML and Excel report.......corrected some real values heading was not getting updated dynamically so I also changed it according to the object type. 9/4/2026->I have sent the mail to the validation team with the required documents for EBOM and DBOM reports, 17/4/26-> • DT_Item –Initial revision date issue fixed • DT_RefItem – Removed 5–6 extra columns • BW_Software – Reports correct • BW_Material – Reports correct • DT_MFGItem – Values proper • ID – Now begins with revision • TTT Product Family – Value successfully retrieved 20/04/2026 - Validation has been completed by swati for Excel & Html | 2026-03-06 | 2026-04-20 | Completed.
Varsha | Phinia | Dx-assembly | Dx-assembly release status issue, fixed | 6/03/2026:- DR connection changes done 10/03/2026:- In some senrio some mix revision id query was failing in certain cases issue is fixed. 11/03/2026:- Testing and latest package need to release. |  |  | Completed
Monish Mattaparty | BW - TEO | Released Document Portal (RDP) | RDP - Recurring Login Issue | 28-Feb-2026: Ghanshyam raised the issue and scheduled a meeting for 04-Mar-2026. 02-Mar-2026: Started analyzing the logs. 03-Mar-2026: Completed log analysis and prepared an initial report. 04-Mar-2026: Ghanshyam has scheduled a meeting today evening. 05-Mar-2026: Connected with Shubham regarding Queries taking 20-40 sec checked SSMS and portal both taking approx. same time also discussed regarding login issue suggested to connect with Manish once. Connected with Manish, discussed regarding that. Tomcat memory and throttle need to check. 06-Mar-2026: Checking logs regarding multiple login sessions. 09-Mar-2026: Developing a solution to logout any previous RDP session than only allow sign in 13-Mar-2026: Need to Test the developed approach. Working on improvising download and zip download to take less memory and not block threads unnecessary 18-Mar-2026: Improvised logs, download and zip download approach. Deployed on QA and informed validation team for testing. 25-Mar-2026: One bug is there fixed it. Need to connect with validation team. 27-Mar-2026: I validated and everything working as expected. 29-Mar-2026: Deployed on Prod. | 2026-02-28 | 2026-03-29 | Completed
Monish Mattaparty | BW - TEO | Title Block - PDF Stamping | TEO CR Enhancement VW frames - Define 3 additional standard frames sizes for the stamping of PDF related to VW drawing sizes (A1, A0 and A0 plus) Stamping is applied, but the text "NOT RELEASED!" is not covered with a white bar / got replaced by a note CONCEPT RELEASED | 30‑03‑2026: Development completed for A1 frame size and to include concept release status for PDF stamping. The changes have been deployed to the QA Dispatcher, initial validation has been completed, and the validation team has been notified for comprehensive testing. 31‑03‑2026: Pratik and Darshna have initiated validation activities. 07‑04‑2026: The validation team has completed validation for the A1 frame size and concept release status. 08‑04‑2026: Inputs required from the customer/client, including A0 and A0 Plus blank PDF sheets and the corresponding CAD templates (A1, A0, and A0 Plus), to extend the functionality for A0 and A0 Plus. 13‑04‑2026: Inputs received from the customer/client. 14‑04‑2026: Working on integrating VW frames along with regular frames. Encountered some issues and currently working on fixing them. 17-04-26 GM Fixed A0 and A0 Plus pdf template issues in stamping code now working fine. planning to push changes on QA env. | 2026-03-30 |  | WIP
Monish Mattaparty | BW - TEO | Released Document Portal (RDP) | Enhance error logs with custom messages | 03‑04‑2026: Work initiated on improving and enhancing log messages. 07‑04‑2026: Development activities have been completed. 08‑04‑2026: Deployed on the QA environment and completed basic testing. Connected with Ghanshyam and informed him about the deployment. 09‑04‑2026: Informed the validation team to proceed with validation. The validation team has completed the validation activities. 13‑04‑2026: The latest changes were deployed to PROD on the night of 12th April 2026. | 2026-04-02 | 2026-04-12 | Completed
Rushikesh Gadkar | BW-TEO | TEO Handler | TEO Handler Update and deployed on QA | 02Feb26-Added new Requirement in TTT DR Status Check, TTT CR status Check,Admin Workflow Check, Remove SAP Equivalent Handler. 05Feb26- Updated CR_Status_Check Handler and deployed on QA environment. Unit testing done by Dev team and asked Validation team to validate all cases of PDS and TEO BU. 07Feb26- DLL Deployed on Production environment. 17 Feb 26- TEO Handler modification for Previous object should get invalid status (presently doing) additionally the pdf under the object should be watermarked as invalid. 23 Feb 26- Mass evaluation TTT Pro - TTT Product family should be capable to get evaluated via the Design Release WF (items with empty value should receive the selected attribute value). Therefore, TTT_DR would need TTT Product Family as attribute and WF handler needs to be adjusted.--Deployed on DEV 02 Feb 26- Expansion of quick release Admin workflow - efficiently move more object types to approved status (today only BW Document) ---compelted | 2026-02-02 |  | Completed.
Harshvardhan Patil | Phinia | CBA- Phinia | 4/07/2026: Working ON CBA customization. Currently developing CBA report as per latest suggestion from Jayant and Ram. Updating utilities as per suggestion from validation team. Pending approver enbled for DO task and deployed on QA. 2/11/2026 : Report Development completed will arrange demo today. Working on CBA command visibility issue. 3/4/2026: Pending Approver validation completed , Will arnage UAT and deploy on Prod. 3/6/2026: Customer Demo scheduled Today. 3/11/2026 : Updated Pending approver code as per comments by Customer and deployed on QA 3/13/2026:QA validation is done and waiting for Prod deployment, DLL is ready 3/25/2026: Responsible party DLL deployed on prod. Deepak : Working on ITK Utility for Dataset Migration: Deepak S: (3/25/2026) Business Logic for Dataset Migration is Done. Working on Error Logging Implementation & Code Optimisation. Deepak S (3/26/2026): Asked to not use the hnj server machines so the development work is halted. 3/27/2026:Started Utility devlopment for CBA 1/4/2026: Two utility devlopment completed. 15/4/2026: CBA tool devlopment completed. Fixed three isues which we got yesterday. |  | 2026-02-04 |  | WIP
| BW/TEO | BW_reponsible_part For BW | Fixing BW_responsible party Code for BW. 3/4/2026: Working with team on TEO customizations requirement. 3/4/2026: BW res party code fix is done will deploy today on DEV, BMIDE deployment is needed for this 3/11/2026: Will planning deployment today on DEV 3/13/2026: Developloymnet completed, still issue is there for export sent logs again to siemens 3/25/2026: Wating for siemense responce on same 10Apr:shared log and code with siemens 15 Apr: Siemens suggested code change that will implement and check
| CLOVER | Handler and AWC | 2/20/2026: Working on Handler and AWC customization for CLOVER 3/6/2026: Working on modifications suggested by Pankaj 3/11/2026: Worked on code modification and shared DLL yesterday 3/13/2026: sheduled meeting with Devanand Today 3/20/2026: Waiting For Ravi's Input 3/25/2026: All changes are done and validation also got completed on QA, will plan deployment on Prod on weekend 3/27/2026: Package shared for Prod deployment |  |  |  | Complete
Nitesh Pawara | Phinia | ITK_ Utility | Development of ITK Utility Code for breaking relation between source and target objects. | 17 Mar-26: As discussed have started working on ITK_Utlity code 20 Mar-26: Work in progress (Around 40% work is completed) 24 Mar-26: Have completed around 70% of work. 26 Mar-26: Need to do some changes in code and perform it on bulk data. 30 Mar-26: Development and Testing of code is completed, need to review with team once. | 2026-03-17 | 2026-03-30 | Completed
Somnath | Phinia | ITK_ Utility | Development "Delete References" ITK Utility | Development completed unit testing completed Utility is completed but creating Generic utility so can be useful for any other requirement to delete the relation bet prim and sec objects | 2026-03-25 |  | Completed
Pratik Khodiyar | Phinia | ITK_ Utility | Utility changing the ownership of non-cad dataset. | Activty completed, need to review with team. | 2026-03-26 | 2026-03-31 | Completed.
Poonam/Subham/Swati | Phinia | ITK_ Utility | Working on utility for change ownership of non-cad dataset | 27 Mar -26 : as per discuss with harshvardhan started working on utility. 30 March -26 - Activity completed , need to review with team. | 2026-03-27 | 2026-03-30 | Completed.
Poonam | TEO | ITK_Utility | working on utility for attribute update | 1-04-2026: as discuss with ganagdhar regarding utility requirement 2-04-2026 : started working on utility for property updation - bwr3_dir_key_merge_dwg - 40% completed 06-04-2026 Completed. Reviewed by Nawaz for testing | 2026-04-01 | 2026-04-06 | Completed.
Nikhil/Ashutosh | Phinia | ITK_Handler | Developement of Rule Handler to check Close/Cancelled status of CI/DR objects attached to CR. | 13-04-2026: Started Working on Handler 14-04-2026: Activity completed. | 2026-04-13 | 2026-04-14 | Completed.
Poonam | TEO | Item Summry Report | Teo CR Enhance -OOTB Item Summary Report | 10-04-2026 - Started working on ootb reports 13-4-2026 - 30% completed 15-4-2026 - 50% completed 16-4-2026 - Completed .Some UI related changes & values are not coming working on that | 2026-04-10 | 2026-04-23 | Completed.

## Support
Resource Name | Project Name/BU | Task Name | Detail Description | Daily Update (Date Wise) | Status (Open/On hold/Completed/WIP) | Start Date | End Date
Pranav\VivekSuraj\Omkar | Selene | Project Selene Ongoing support | Working on the daily ticket queue on Service now and assisting the TEO hypercare members with issues reported. | 4/21/2026: INCIDENTS-66(WIP) , SCTASK-44(WIP) PLM Queue 4/2/2026: INCIDENTS-57(WIP) , SCTASK-52 (WIP) PLM Queue 3/5/2026: INCIDENTS-51 (WIP) , SCTASK-41 (WIP) PLM Queue | WIP | 2025-09-22 | Till Date
Pranav /Rushikesh/Somnath/harsh | Selene | Project Selene Ongoing support | INC0279693 : CR*6003& 6533 cannot be closed. Also reporetd by Joanne and DIlip | 2/10/2026: Handler placed on Close CR earlier during Selene project was DR_CI_STATUS_CHECK_HANDLER which was working fine. During TEO Go live, CR_Status_Check handler was introduced for TEO which had issues .After debugging the code and testing it on QA was pushed to production and now the issue is fixed. | Completed | 2026-01-21 | 2026-02-03
Pranav/Somnath/Praveen | Selene | Project Selene Ongoing support | INC0271454 : DR is released. skipped the mandatory approvals stages (Peer Review and Designer Prepare for release) - DR000005556 | 2/10/2026: The issue was not reproducible on QA when we tested it from our end. On 4th Feb 2026, we had a session with user in which we ran this PDS DR flow entirely with the help user and got to know that they were removing or replacing the the task assigned at design prepare for release task due to which the task was getting skipped. When followed the right process, the flow was working fine and the user is convinced now. | Completed | 2025-10-27 | 2026-02-05
Pranav/Vilas/Pranay | Selene | BOM Consolidation Support | INC0280192 : EBOM Quantity Mismatch – 42007836/003 children Part qty are showing 1 Each instead of the qty per "42007836_EBOM_C/001 (Archive.PDS)". pls update–42007836/003 | 2/10/2026 : Such cases are reported once in 2 months by SIngapore users. For such cases we had word with Mark and Mark suggested if the frequency is less then lets fix it manually. Currently this can be done through csv to tcxml.In touch with Migration team ( Vilas & Pranay) | Completed | 2026-01-27 | Expected to close by today
Pranav/Praveen | Selene | Smart Team to 1PLM user data issue | INC0279831 : We have noticed same repeating problem for the JT file creation for the PN's 1NA001364-0, 1NA001365-0, 1NA001366-0 & 1NA001367 | 2/10/2026: Need to check with Praveen as some of the JTs are not getting created for solidworks datasets even though the dispatcher services are up. Log filesshow no major error. 2/17/2026: When done global search the JTs were created but were not attached to the Item with rendering relation. User suggested to attach the same and now the issue is closed. 2/26/2026: The RCA of the same is done and in the logs the error found is PhoneHome error 0 while ProNotificationSet status 0. There are some changes needed to be done in the IPEM xml file post that this can be surpassed. In touch with Praveen to make the changes in IPEM for the same. | Completed | 2026-01-22 | Expected to close by this week
Pranav/Bhau/Gopal | Selene | Project Selene Ongoing support | INC0266580 : We observe that since some time, when new Packaging Instruction is sent to SAP, there is no data in the field of Short Text. | 2/10/2026: We had a call with Gopal (BW SAP Support Team) and based on the discussion we found that some parameters in T4S will have to be changed. 2/26/2026: This will have to be converted into SCTASK but 3/4/2026: Paulina still not convinced . Planning to have a call with Praveen and push this to Plan & Build team | Completed | 2025-09-12 | Expected to close by this week
Pranav/Ghanshyam/Praveen | Selene | Project Selene Ongoing support | INC0274119: The summary email indicated that the Final Review task is missing reviewer approval and is currently displayed as ‘No Decision". see attached | 2/10/2026: The mail notification for some DR instances are not providing proper results. Checking on it with Praveen and Ghanshyam. 2/17/2026 : Had a call with Jaonne. Seems like this issue happened due to some network glitch as all the latest DR mails didnt have such issues.As the issue is not reproducible closing this case | Completed | 2025-11-20
Shashi | TEO | Project TEO Ongoing support | INC0281297 : Urgent: Character Limit Issue in BW Properties “Based On” Field | 2/24/2026: this change will be done in upcoming block point. 2/10/2026: Currenly the Based on Property in BW properties is having character limit (14) and the user is expecting to increase it.User will have to check with Stefen Knoob and decide on the same 2/26/2026: This will be considered as a CR request. Based on the CR approval only this will be considered as a Block point request. 3/31/2026: Considered this for CR request. | Enhancement | 2026-02-05
Pranav/Krutika | Selene | Project Selene Ongoing support | INC0281095: User creation from BW user portal failing. | 2/10/2026 : checking the user request and testing same with Krutika to find the rootcause. | Completed | 2026-02-04 | Expected to close by this week
Pranav | Selene | Project Selene Ongoing support | INC0280414 : When the "Reason for Change" and "Proposed Solution" were updated in the Change Request (CR), the corresponding fields in the Design Record (DR) did not update as expected | 2/17/2026: Testing the flow to anyalyse the same . 2/26/2026: Currently the issue is not reproducible on QA. Analysing some more DRs on prod to verify the same. | Completed | 2026-02-14 | Expected to close by this week
Vishal | Solero | Teamcenter Down | TC was down due to some issue of LDAP server. User was not able to login into TC. Solero LDAP and Network resolve the issue. Issue highlighted to Brett (Engineering Head) |  | Completed | 2026-02-02 | 2026-02-03
Pranav | Selene |  | SCTASK1086803: Installation tickets SCTASK1085756: TC installation SCTASK1084667 : TC Installation SCTASK1084632 : 1. Creating my Team center ID 2. Installing Teamcenter application 3. Installing CATIA for CAD integration (CATIA R32-TCIC integration) 4. Installing DSLS for CATIA (DS license server) : License location NABLTCAD1851 5. Installing SpinFire Ultimate SCTASK1084027: Access to Teamcenter and NX | 2/17/2026" checking with vishal and gourav on the samel | Completed
Pranav | Selene |  | SCTASK1084723: User db account not created | 2/17/2026 : Hello Fei, Qiying, Seems like your account is not created yet. Kindly use the below link to raise a user creation request: http://azruse2tcprutil.global.borgwarner.net:8080/BW_UserManagementSystem/ Based on your location selection in the form, approvers will be alloted to your request. Post their approval in the system your user will be created automatically. Reach me out if you have further concerns | Completed
Pranav | Selene |  | INC0283342: Dashboard creation discrepancy, fields/values are not populating | 3/10/2026 : Currently trying this use case and its feasibility in QA. Post that only can decide whether this is possible or if not can be considered as an enhancement request. 3/31/2026: based on the siemens IR, custom properties like design site and customer program were checked with filterable and indexing options through BMIDE and deployed but still the results are not achieved. A followup meeting with concerned siemens person will be scheduled today or tommorrow based on his availability. 4/9/2026: As per the Siemens IR update, the configuration is update d in the system. Awaiting user response on the same. | On hold | 2026-02-26 | Planning to close this week.
Vishal & Gourav | BW MCAD | Ticket | All the tickets are on track and close on time and maintain SLA. Currently 18 tickets are open and in WIP | 21-Apr-2026: 82 Tickets Closed, 32 active, no critical issues | WIP | 2026-02-09 | Till Date
Omkar | BW MCAD | Ticket | Supporting Vishal in MCAD ticket handling for BW on ServiceNow |  | Completed | 2026-02-09 | 2026-02-09
Somnath | BW Selene | Ticket | Issue coming to users task is getting skipped | 3/5/2026 : Issue is fixed. Confirmed with Praveen. | Complete | 2026-02-02 | 2026-02-03
Somnath | BW TEO | Ticket | Error coming while clsoing CR - found root cause need to check in custom handler | 3/5/2026 : Issue is fixed. Confirmed with Praveen & user | Complete | 2026-02-03 | 2026-02-04
Krutika\GM\VC\PN | Selene\TEO | Incorrect group created in PROD and QA | Incorrect groups in TC organization are getting created by utility ? | 3/5/2026: Krutika is checking with Pankaj on this issue with user management portal. 2/11/2026 Issue discussed in call. Need to do RCA. 3/10/2026: Checked with Pankaj. He sugested some use cases to check whether this is happening through user db only 3/17/2026: Krutika is enabling the logs for user DB. Post that the code will have to be further checked in detail to check the user transaction 3/31/2026: The logs are enabled for the user db transactions. Currently things are under observation. If any such similar case arises, we may try to investigae and analyse based on the log details to debug further. 4/9/2026: Recently no issues observed. Logs enabled for the verifcation of the same | On hold
GM\VC\PN | TEO | JT not getting attached to Item Rev | Use case 1 : JT getting created but not getting atatched to item rev | 3/5/2026 : this issue is fixed on prod. There is a seprate issue with JT creation while in workflow. Prepare RCA after and before changing the ACL. 2/26/2026 : Unable to reproduce to this issue on PROD now. 2/24/2026 : Still working on this issue 3/10/2026: RCA been done By ganagadhar on QA. | Complete
|  |  | Use Case 2 : JT creation for new part when tested on Prod goes into terminal . | 3/10/2026: The RCA of the same is done and in the logs the error found is PhoneHome error 0 while ProNotificationSet status 0. There are some changes needed to be done in the IPEM xml file post that this can be surpassed. In touch with Praveen to make the changes in IPEM for the same. | Complete
| TEO | JT not getting attached to Item Rev | Use case 3 : JT causing error when the CAD part is part of the workflow | 3/10/2026: Praveen testing the same . (Adding dcproxy to Workflow ACL) 3/17/2026: Identified the rootcause. The Workflow ACl is now placed in TTT workflow for the same | Complete
Vivek | Selene | TOE* DT Item Rev | INC0282889: DT Item Rev with BW_MIG and DBA group ownership | 3/10/2026: As discussed with Ravi, assigned to Plan and Build team. 3/5/2026: Got approval from Eric for changing ownership of such data. 2/26/2026: checking with Pankaj and Pasha about the migration status of these ID's. 2/24/2026 : Looks like migrated data | Completed
Pranav | TEO |  | INC0286296: dr00006138 workflow i can't be able to submit, some error appear, could you please resolve this issue. | 4/9/2026: The issue occured because the user has manually added an additional user in review 2. After the removing the additional user, the select signoffs requirement was fulfilled and the user was able to perform asction on the workflow task. | Completed
Pranav |  | Project Selene Ongoing support | INC0285584: The Summary Report (email) and TC approval status are inconsistent. The Summary Report indicates that the user did not approve, | 3/31/2026: Need a round of trial on QA again as this is coming for some instances in prod. Rootcause still unknown 4/9/2026: Tested on QA, couldnt be reproduced. There are some instances in prod been reported . Scheduled a call today to test a DR in prod infront of the user to check and analyse the same. | On hold | 2026-03-24
Gangadhar | BW TEO | BW- Teamcenter: Team Center Released Drawing Portal | INC0282920 - The Team Center Released Drawing Portal is very slow. It take 20-30 seconds to return a search. This is not productive when I have to lookup serval drawings to verify something. | 15 | WIP
Gourav | MCAD | (CATIA) Q-CHECKER with TTT configuration- Create access | INC0287238: USers need to have the Q‑Checker configured to work in the TTT environment, so that they can take full advantage of all the benefits this tool provides | 13/04/2026: It may need to do some configuration changes with Centiflex, hence awaiting Nikhil Bele`s support on this. 15-04-2026: There is no Qchecker environment in TTT confirmed with Nikhil and conveyed to customer. | Completed
Vivek | TEO | Unable to open data in TCIC | INC0287228: Unable to open data in TCIC | 4/21/2026 : checking for license issue. | WIP

## Validation
Resource Name | Project Name | Task Name | Detail Description | Daily Update (Date Wise) | Start Date | End Date | Status (Open / On hold / Completed / WIP) | Remark | Document Links | Sequence of Team Members who will present validation status
Ekta,Nitesh,Yuvraj | TEO | TEO Hypercare |  |  |  |  | Complete | 23-feb-26: Inprogress =1 , pending =3, total=105 16-feb-26: Inprogress incident 48, sctask - 65, pending- 31 12-Feb-26: Approx 50 tickets (Incident & Sctask) in WIP state. 06-Feb-26: Approx 40 tickets (Incident & Sctask) in WIP state. |  | Vivek
Nitesh,Yuvraj | TEO | QA Deployment Validation |  |  | 2025-11-17 | Till Feb13 | Complete | 02-Feb-26: Validation complete |  | Ekta
Ekta,Nitesh,Yuvraj | TEO | Ticket TAG assignment |  |  | 2026-01-30 | 2026-02-02 | Complete | 30-Jan-26: Complete |  | Pratik
Omkar | N\A | CAD Validation Training |  |  | 2026-01-30 | 2026-01-30 | Complete | 30-Jan-26: Complete |  | Poonam
Suraj,Omkar,Vipin,Darshna,Pratik | TEO | QA Deployment Validation-round 2 |  |  | 2026-01-30 | 1 week | Complete |  |  | Swati
Rajdeep | N\A | EBOM Validation Training |  |  | 2026-02-02 | 2026-02-02 | Complete |  |  | Chaithanya
Vipin | N\A | Autovalidation Internal Training |  |  | 2026-02-02 | 2026-02-02 | Complete |  |  | Rajdeep
Darshna\Pratik | Phinia | CBA Training Document Preparation |  |  | 2026-02-03 |  | Completed | 22-april-26: Completed,,mailed the document for the internal review. 20-april-26- 90% complete. 1 use case pending. 14-april-26- Working on the new changes suggested by Harshvardhan. 24-march-26 CBA document draft shared with Harshavardhan. Will make changes as necessary after his review & further discussion with him. 24-feb-26: Created as baseline. On-hold due to requirement changes. |  | Darshna
Ekta,Nitesh | TEO | TEO ticket resolution documentation |  |  | 2026-02-03 |  | Cancelled | 23-Mar-26:Will connect with Gangadhar for latest changes need to be execute for this activity. 20-Mar-26: Some additional changes need to do so this acitivity is keep on hold. 16-Mar-26: 90% is completed and current progress status will be shared throuh mail to Team 09-Mar-26: submitted FAQ doc. This doc is not required. 06-Feb-26: document preparation in progress. 16-feb-26: currently this activity is on hold. 23-feb-26 : 50% completed 26-March-26: Gangadhar is preparing separate document for this activty. Kep on-hold from validation side. |  | Vipin
Validation Team | TEO | TEO AWC FAQ Document |  |  | 2026-02-04 | 2026-02-23 | Complete | 04-Feb-26: Gangadhar has already prepared such kind of document. Will check if we need to add anything. |  | Omkar
Validation Team | TEO | DLL validation on QA ENV |  |  | 2026-02-04 |  | Complete | 05-Feb-26: 1st round of validation is complete. Material.TTT group was unable to link the DR. 06-Feb-26: Need to revalidate changes because of new changes in dll deployed today morning. |  | Nitesh
Aviraj | TEO | Release Portal Doc Validation |  |  | 2026-02-05 | 2026-02-06 | Complete | 05-Feb-26: Unable to find specific data required for this validation. Checking with GM and Monish. 06-Feb-26: This activity is completed & result is informed to Gangadhar |  | Suraj
Darshna,Pratik,Omkar | TEO | TEO QA Catia issue validation | JT migrated at assembly level is creating seprate entry product in Catia assembly. Simens suggested TC pref to disable it. |  | 2026-02-05 | 2026-02-06 | Complete
Omkar | MCAD | Support - ServiceNow Ticekts | Supporting Vishal Kadam in absence of Gourav Tiwari |  | 2026-02-09 | 2026-02-26 | Complete | 23-02-2026: Tiotal 84 Tickets in last week. 11 active yet (Incidents + SCTasks). Nothing critical. 26-Feb-2026: 91 Tickets Closed, 12 active, no critical issues
Ekta,Nitesh,Yuvraj | TEO | AWC FAQ document | TEO specific AWS FAQ Doc Prep |  | 2026-02-11 | 2026-02-20 | Complete | 90 % Document preparation is completed, awaiting for Gangadhar's reviews and suggestions. 20-feb-2026: completed and shared with team
Omkar,Darshna,Pratik | TEO | Item Revise Issue (BVR Sync Issue) | Item Revise Issue (BVR Sync Issue) |  | 2026-02-25 |  | Cancelled | 25-Feb-2026: As per Pasha, RUN team is validation this.
Omkar,Darshna,Pratik | TEO | NX PDF creation and Stamping testing | NX PDF creation and Stamping testing |  | 2026-02-20 | 2026-02-25 | Complete | Still in development phase 23-feb-2026: Still testing is going on. 25-feb-2026: Validated pdf stamping functionality with "XYZ_TTT_Design" and "XYZ_TTT_Status" Process,working as expected.
Omkar,Darshna,Pratik | TEO | PDF stamping for Invalid status | PDF stamping for Invalid status |  | 2026-02-18 | 2026-02-20 | Complete | We tested for DT_Item and DT_Mfgitem and shared report over mail
Vipin / Rajdeep / Suraj / Omkar | Selene | T4S Delta BOM SAP transfer on DEV Env.. | Delta BOM SAP transfer validation for Selene. No TEO impact. |  | 2026-02-25 |  | Complete | 16/3/2026: Informed Failed case to Bhau. Bhau is checking With Ram. 13/3/2026: As confirmed by SMEs , BOM Usage Update frequently changes the values and it must reflect in SAP BOM transfer and this particular use case is FAILING while Validatiing Use case.Waiting Bhau and Ram comments on this particular Use case. 9/3/2026: Bhau & Ram are checking with customer for 'BOM usage' issue (Use case No.09). 6-3-2026: Team has completed Validation and sent mail notification. Checking BOM usage failed case with bhau 4-3-2026: Remaining use case is still validating by team. for existing SAP data use case, found fail WF status, need to discuss with Bhau. 25-2-2026: Usecase-1 completed, remaining Use case is still to test 27-2-2026: Out of 14 use case, 5 use case validation completed. 1 Error reported to bhau. remaining use case testing is going on.
Rajdeep\Swati | Phinia | BOM Export Validation (DEV ENV) | BOM Export validation for Phinia |  | 2026-02-24 | 2026-02-06 | Complete | 05-03-2026: Shubham's update- the data mismatch issue was due to the server SBX1 & SBX2 sync issue - validated and passed 04-03-2026: another issue for Part Data Extraction report issue (object type difference/mismatch) issue reported to Shubham, 02-03-2026: 2 issues (Item Name column and Release status mismatch) found and reported to shubham 03-03-2026: 1 issue (item name) resolved by Shubham validated and working as expected and for 2nd issue release status shared another ID which having the same issue
Suraj\Pratik\Nitesh | Phinia | 1) Part Numbering validation | Phinia CR validation for Naming rule changes |  | 2026-02-26 |  | Cancelled | 23-03-2025: Update from Nikhil N that this deployment or changes are not considered and not deloyed, hence making this activity as cancelled. 12-Mar-2026: This activity is on hold/cancel, until further notice 11-Mar-2026: NX, Catia, Solid Works completed and working as expected. Creo is pending. 09-Mar-2026: Need admin rights to toggle. 05-Mar-2026: NX CAD complete. Creo and Catia , SW pending due to env switcher. 04-Mar-2026: Getting help from Mangesh to switch env. Also checking with Kuldeep for his admin ID reactvation. 27-Feb-2026: Have started the validation, from AWC side for Design Item type validation is completed and since for EDA Design Doc old naming rule is attached so some scenario are getting failed and have reported to Somnath.
Ekta,Nitesh | TEO | TEO Hypercare Extension | TEO Hypercare extension till March |  | 2026-02-13 | 2026-03-30 | Complete | 30-3-2026: TEO hypercare finished. 24-Mar-2026: In Progress(Incidents) =2, Pending=3, Resolved=3, Closed= 148 16-Mar-2026: No Critical issues , In Progress(SCTask) =3, Pending=2, Resolved=16, Closed= 124 12-Mar-2026: In Progress(SCTask) =1, Pending=2, Resolved=15, Closed= 119 09-Mar-2026: In Progress=4, Pending=2, Resolved=7, Closed= 112 5-Mar-2026: In Progress=4, Pending=2, Resolved=4, Closed= 110
Chaithanya\Poonam\Yuvraj | Phinia | 2) CR validation | Phinia CR validation for Naming rule changes |  | 2026-02-26 |  | Complete | 27-Feb-2026: Have started the validation, from AWC side for Design Item type validation is completed and since for EDA Design Doc old naming rule is attached so some scenario are getting failed and have reported to Somnath. 26-Feb-2026: Will setup call with Somnath and discuss requirements 02-Mar-2026: "Pending Approver" validation is in progress, export to excel for change objects is working fine.
Nitesh\Yuvraj\Chaithanya\Suraj | Phinia | responsible party reports | Responsible party reports |  |  |  | Complete | 16-03-2026, As per the new request completed the validation " Last columns are as per the release status.. release date is entered in respective release status column" 09-Mar-2026: Need to hold this activity since Shubham has received new requirements which needs to be incorporated. 09-Mar-2026: 90% complete. Pending approver attribute value not coming as expected. 5-Mar -2026: Today morning we have discussion with shubham and have completed 50% validation, no issues found yet. 4-Mar-2026: We have not started the validation activity yet, once development is completed by shubham will setup a call with him for demo to understand the usecases.
Darshna,Pratik | TEO | PDF stamping for Invalid status | PDF stamping for all applicable release status |  |  |  | Complete | 3/9/2026: completed. 06-03-2026; Manifestation relation is completed and some release status of rendering is pending
Omkar | Symbotic | Walkthrough sessions & Consultation documents | Study of As-Is process & consultation for PLM based improvements. Prepare teh GAP-OFI documents based on these discussions. |  | 2026-03-23 |  | Complete | 20-April-2026: Most of the tasks are being handled by BHavtesh, Piyush, Kuldeep now. 13-April-2026: Workshops are over. As is presentation is prepared. Team will be working on the To-Be solution document this week. 08-April-2026: Recent workshop MOM, GAP-OFI & As-is process slides. 06-April-2026: Followup - Walkthrough sessions. Working on the GAP-OFI
Poonam | TEO | Item Custom Report Builder-QA Env | Item Custom Report |  | 2026-03-12 |  | Complete | 7-4-26: 100 % completed. review is pending with Gangadhar. 12-March-26 :as discuss with gangadhar have started exploring on TEO Item Custom Report 13-March-26 : started working on Item Report 14-March-26 - 50% completed 20-march - We are changes new custom coloum in reports 30-March : got input from gangadhar so we are updating according in report 31-March : 50% completed 06-April-2026: 80% completed. 09-Aprill-2026 : completed. Unit testing doing Subham
Chaithanyasai | NA | Pending Approver Attribute validation internal training |  |  | 2026-03-11 | 2026-03-11 | Complete
Chaithanyasai | DANA | Auto Validation(DB to DB Compare) | Auto Validation for Source DB to Target DB Validation |  | 2026-03-12 |  | Cancelled | 16-03-2026, Development Phase. Testing is done on existing sample data. Waiting for the confirmation to test on Real Data
Nitesh | Phinia | ITK Utility for Relation Delete | Development of ITK Utility Code for breaking relation between source and target objects. |  | 2026-03-17 | 2026-03-30 | Complete
Vipin / Suraj | Selene | T4S Delta BOM SAP transfer on QA Env.. | Delta BOM SAP transfer validation for Selene. No TEO impact. |  | 2026-03-18 |  | Complete | 16-4-26: Validation completed. sent mail to team members 15-4-26: Validation is WIP. 14-4-26: Connected with Bhau, collected new requirement use cases. we will complete validation on QA . 13-4-26: we will connect with Bhau to understand new requirement use case and start validating new use case today. 30-3-26: User has requested more requirements, Bhau is working on it.(30-3-2026 to 10-4-2026 on HOLD) 26-3-26: Validation Completed. sent mail to all members. Bhau is checking BOM usage failed case with SME. 24-3-2025: Out of 15 use case, 10 completed , remaining Use case validation is WIP 20-3-2025: Out of 15 use case, 10 completed , remaining Use case validation is WIP 19-3-2025: BOM usage Property Update is failing same as DEV env. Bhau will check with SME and update this use case
Chaithanya / Nitesh/Poonam/Swati/Pratik/Darshna | Selene | RDP Changes Validation on QA Env.. | latest RDP Changes Validation on QA Env.. |  | 2026-03-19 |  | Complete | 20-3-2025: Team has validated discussed scenarios and there is no Issues found. Validation status has sent to mail to all members
Nitesh | TEO | Hypercare FAQ document | Alignment of Hypercare FAQ document |  | 2026-03-31 | 2026-04-03 | Complete | 3-4-26: Have reviewed and checked the document, also updated the table of contents links. They are now working correctly.
vipin/chaithanya/pratik/nitesh | TEO/Selene | Bolock Point- 57 Deployment On Production |  |  | 2026-03-28 |  | Complete | 28-3-2026: Validation completed by team. All discussed Use case is reflected on 1PLMPROD env..
Darshna\Omkar\Swati\Ekta | Phinia | DR Validation activity |  |  | 2026-03-28 |  | Complete | 29-3-2025: all cad integrations working fine except Catia is not generating pdf.
Darshna/Pratik / Omkar | Phinia | Validation test cases for CBA Alignment migration. | Validation test cases for CBA Alignment migration. |  | 2026-03-26 | 2026-04-13 | Complete | 13-4-26: 100% Complete. Internal review pending 8-4-26: completed 50% 6-4-26: CBA walkthrogh done . team is preparing test case documents 1-4-26: CBA walkthrogh done . team is preparing test case documents 30-3-2026: Going thru the document. 15-april-2026:Completed | CBA_Alignment_Test_Cases.xlsx
Rajdeep\Aviraj\Swati\Nitesh\Ekta\Poonam | TEO | TEO Enhancement Requirements | Test Cases for TEO Enhancement Requirements |  | 2026-03-30 |  | Complete | 4/10/2026 100% completed. 6-4-26: 90% draft version completed. 1-4-26: rajdeep and swati has completed drft version. rest of the team members are updating test case 30-3-2026: Going thru the document. | TEO – Enhancements Requirements
Suraj\Vipin\Chaithanya | TEO | TEO Enhancement Requirements | Test Cases for CR Document for Prototype Parts Transfer to SAP |  | 2026-03-30 |  | Complete | 1-4-26: Draft version of test case completed. 30-3-2026: Going thru the document. | SAP_Enhancement
Darshna\Pratik | TEO/Selene | TEO Enhancement Requirements | Title Block - PDF Stamping - CR/ER - QA Validation-for Concept release status |  | 2026-03-31 | 2026-04-03 | Complete | 4/8/2026 Completed. 6-4-2026: it will be completed by today 2-4-2026: Pending with few more release statuses 31-3-2026: started PDF stamping activity. | PDF_Stamping_TEO.xlsx
Rajdeep\Swati | Phinia | BOM Export Validation (QA ENV) | BOM Export validation for Phinia |  | 2026-03-25 | 2026-03-30 | Complete | 30-3-2026: Report shared with Shubham for review. (No issues found)
Nitesh | Phinia | Test cases for Pending Approver Report | Test cases for Pending Approver Report |  | 2026-03-26 | 2026-04-02 | Complete | 2-4-26: Have completed the test cases document for the Responsible Party Report
Poonam | TEO/Selene | TEO Enhancement Requirements | Working on update property utilty |  | 2026-04-02 | 2026-04-08 | Complete | 8-04-2026 Completed. Reviewed by Nawaz doing unit testing on QA 6-04-2026 - It will be completed today. 2-04-2026 : started working on utility for property updation - bwr3_dir_key_merge_dwg - 40% completed 1-04-2026: as discuss with ganagdhar regarding utility requirement
Vipin\Chaithanya\pratik\darshna | Phinia | phinia CBA Utility ITK Testing | Phinia CBA Utility to update design revision associated non cad Dataset Change Ownership ITK Testing |  | 2026-04-03 |  | Complete | 09-04-26, Tested the utility and it;'s working as expected 6-4-26: ITK utility Observation shared with team. 3-4-26: use case testing completed , shared observation with team.
Vipin\Chaithanya\pratik\darshna | Phinia | phinia CBA Utility ITK Testing | Phinia CBA Utility to update Document Revision and all secondary Dataset Change Ownership ITK Testing |  | 2026-04-14 |  | Complete | 15-4-26: Issue is fixed by somnath. now utility is working fine. 14-4-26: Issues shared with Somnath. Somnath is working on it
Vipin\Chaithanya\pratik\darshna | Phinia | phinia CBA Utility ITK Testing | Phinia CBA Utility Relation Delete ITK Testing |  | 2026-04-03 |  | Complete | 09-04-26, Tested the updated utility and it;'s working as expected 08-04-26, Tested the utility and it;'s working as expected 6-4-26: ITK utility Observation shared with team. 3-4-26: use case testing completed , shared observation with team. | CBA_ITK_Utility_Testing
Vipin\Chaithanya\pratik\darshna | Phinia | phinia CBA Utility ITK Testing | Phinia CBA Utility Update Status on Revision and datasetsITK Testing |  | 2026-04-03 |  | Complete | 09-04-26, Tested the utility and it;'s working as expected 6-4-26: ITK utility Observation shared with team. 3-4-26: use case testing completed , shared observation with team.
Nitesh\Chaithanya | Phinia | Validation of Pending Approval for DO task on QA environment | Validation of Pending Approval for DO task on QA environment |  | 2026-04-06 |  | Complete | 4/8/2026: completed. 6-4-26: Team has started to validate it. | https://tatatechnologies.sharepoint.com/:f:/r/sites/BorgWarnerProject/Shared%20Documents/Delivery/Project_Pathfinder/Internal/08_Validation/TEO%20(SAP-PLM%20)/TEO%20%E2%80%93%20Enhancements%20Requirements/UAT?csf=1&web=1&e=uSGPdy
Rajdeep\Vipin | TEO | TEO Enhancement Requirements | User Feedback sheets for TEO CR UAT(Template) |  | 2026-04-08 |  | WIP | 21-4-2026: As per the suggestions from the Gangadhar making the changes in UAT sheet 20-4-2026: checking with Gangadhar for data input. 13-4-2026: Darft is ready, data specific review pending with Gangadhar. 8-4-2026: Working on TEO Enhancemnet UAT Sheet Templates.
Swati\Nitesh | TEO | TEO Enhancement Requirements | BOM reports - EBOM/DBOM report according to a TTT requirements |  | 2026-04-10 |  | Complete | 21-4-2026: Validation is Completed For Excel Report on QA Env. Working as expected to requirements. 20-4-2026: received email for excel report validation. WIP 17-4-2026: validation complete for html report. Excel report pending. 16-4-2026: DT_item BOM Report Issues reported to Subham 15-4-2026: Working on revalidation of TEO Enhancement DT_Item and DT_MfgItem BOM Reports. 15-4-2026: Validation is completed on QA Env. Working as expected to requirements. 14-4-2026: 70% Complete. 13-4-2026: 30% Complete. IDs for testing requested to Subham. 10-4-2026: Working on TEO Enhancemnet BOM Reports
Poonam\Ekta | TEO | TEO Enhancement Requirements | RQ-TE-02-2.9: OOTB Properties validation on DEV |  | 2026-04-10 | 2026-04-13 | Complete | 13-4-2026: Validation is completed on Dev Env. Working as expected to requirements.
Ekta\Nitesh | TEO | TEO Enhancement Requirements | RQ-TE-02-2.7/2.8: Workflow Validation on BW DEV env. |  | 2026-04-10 | 2026-04-17 | Complete | 17-4-2026: Validation done for DT_Item and DT_MfgItem on dev enviroment. 15-4-26: completed , 2.8 will be done in sprint_2 10-4-2026: 50% complete. Working on rest. | Validation_Reports
Nitesh\Ekta | TEO | TEO Enhancement Requirements | RQ-TE-03-3.7: Workflow Validation on BW DEV env. |  | 2026-04-10 | 2026-04-13 | Complete | 10-4-2026: Started. 10% Done. 13-4-2026: Validation activity is completed on Dev Env. No issues found
Chaithanya\Suraj | TEO | TEO Enhancement Requirements | REQ_CR26-01-015---Sync Prototype Release to SAP - Design Release workflow |  | 2026-04-10 | 2026-04-13 | Complete | 13-4-2026, Validation is completed on Dev Env. Working as expected to requirements. 10-4-2026: started | TEO_Sync_Prototype_to_SAP_Validation_Status.xlsx
Chaithanya\Nitesh | TEO | TEO Enhancement Requirements | REQ_CR26-01-002 ---TTT DR Validation Reports |  | 2026-04-13 |  | WIP | 21-04-26, Re-validated 1. Additional Review is fixed . 2. TTT Project ID is not fixed 3. Search Criteria With Date Created and Date Released is fixed 17-04-26, Re-validated 1. Additional Review is Fixed values are populating correctly only on Html report (which displays in AWC), But when try to download Excel report (Locally download) is not fixed and it showing this value in Excel report "The variable 'bwr3_additional_review' is not defined." 2. Value "TTT Project ID" is not coming on report and downloaded excel. 3. Search Criteria With Date Created and Date Released results are not fecthing in the report. 14-4-2026: Vaidated on QA. Bugs reported. Attributes ( TTT Project ID and Additional Review were not populating in the report) Search Criteria With Date Created and Date Released results are not fecthing in the report. shared observations through Mail 13-4-2026: Yet to start, Demo is pending from DEV team. | TEO_DR_Summary_Report_Validation_Status.xlsx
Chaithanya\Ekta | TEO | TEO Enhancement Requirements | REQ_CR26-01-002 ---BW_Maturity_Shift_Rev Report |  | 2026-04-13 |  | WIP | 21-04-26, Re-validated 1. TTT Project ID is not fixed 2. Search Criteria With Date Created and Date Released is fixed 17-04-26, Re-validated 1. Except TTT Project ID , remaining attributes are populating in both Html report ( display in AWC) and Excel report (Locally download) 2. Search Criteria With Date Created and Date Released results are not fecthing in the report. 15-4-2026: Vaidated on QA. Bugs reported. Attributes ( TTT Project ID, External References, Additional Review, Disposition, Maturity and Closure values were not populating in the report) Search Criteria With Date Created and Date Released results are not fecthing in the report. shared observations through Mail 14-4-2026: Yet to start | TEO_BW_Maturity_Shift_Rev_Report_Validation_Status.xlsx
Pratik | Phinia | CBA Functional Validation On Phinia QA Environment | CBA functional Validation On Phinia QA Environment |  | 2026-04-13 |  | WIP | 20-4-2026: 1 Bug Reported related to AWC functional validation. CAD side funct. validation complete. 17-4-2026: 1 Bug Reported related to AWC functional validation. 15-4-2026: CAD side 80% complete 14-4-2026: AWC side 50% complete 13-4-2026: Got confirmation for QA today. Will start today.
Darshna | Phinia | CBA CAD Validation On Phinia QA Environment | CBA CAD Validation On Phinia QA Environment |  | 2026-04-13
Darshna/Pratik | Phinia | CBA Validation On Phinia QA Environment | Migration Validation for CBA On Phinia QA Environment |  | 2026-04-13 |  | On-Hold | 14-4-2026: waiting for confirmation from Migration team
poonam/Rajdeep | TEO | TEO Enhancement Requirements | REQ_CR26-01-007 - Permissions for Administration.TTT Global Doc Admin and Doc Controller: ACL Validation on BW QA Env... |  | 2026-04-13 |  | Complete | 13-4-2026: Validation is in progress, one observation is shared with Gangadhar (able to do the Revise operation on the objects) and waiting on the updates from him.
Ekta\Nitesh | TEO | TEO Enhancement Requirements | REQ_CR26-01-012 - Drawing Number Evaluate all T&E migrated DT_Items and DT_MfgItems |  | 2026-04-15 |  | Complete | 15-4-2026: Validation completed for sample of DT_Item and DT_MfgItem ids. functionality is working as per the requirements.
Nitesh | TEO | TEO Enhancement Requirements | REQ_CR26-01-005 - Rerun Stamping process workflow |  | 2026-04-15 | 2026-04-15 | Complete | 15-4-2026: Have completed the validation. No issues were found, and the functionality is working as per the requirements.
Ekta\Nitesh | TEO | TEO Enhancement Requirements | REQ_CR26-01-010 - Drawing SAP Dir key update (Differentiate 2D & 3D data from the migrated data) |  | 2026-04-16 |  | Complete | 16-4-2026: WIP 17-4-2026: Validation done for sample of DT_Item and DT_MfgItem
Pratik | Phinia | Phinia G3.2 Change Object Validation on QA DR->CI | Phinia_G3.2_ChangeNotice_Validation |  | 2026-04-16 |  | Complete | 16-4-2026: Validated Metadata,relation,dataset, one issue found that dataset named ref file size is missing in QA and pranay is fixing this issue. Revalidated issue is fixed.
Ekta | TEO | TEO Enhancement Requirements | REQ_CR26-01-006: Quick release workflow access for global document admin role: ER for Legacy Thermal Workflow – Release status change |  | 2026-04-21 |  | WIP | 22-4-2026: Validation is going on for sample of object type. 21-4-2026: Validation started
Darshna/Pratik/Rajdeep | Phinia | Phinia G3.2 CBA functional and CBA Migration use case UAT Sheet Prep | User Feedback sheets for Phinia G3.2 CBA(Template) |  | 2026-04-21 |  | WIP | 21-4-2026: WIP
Nitesh/Rajdeep/swati | Viper-IP | Viper IP : Generic use case Test case Prep(Teamcenter and Integrations) | Generic Use case Test Case sheets for Viper-IP |  | 2026-04-21 |  | WIP | 21-4-2026: WIP
Darshna/Pratik | TEO | TEO Enhancement Requirements | REQ_CR26-01-001 - Title Block - PDF stamping for additional frame sizes (A1, A0 and A0 plus) - CR/ER - QA Validation |  | 2026-04-22 |  | WIP | 22-4-2026: WIP
Nitesh | Viper-IP | Project Assign ITK Utility | Testing of Project Assign ITK utility code |  | 2026-04-20 | 2026-04-21 | Complete | 20-4-2026 : Have recompile the code, need to test it. 21-4-2026: Have completed testing and code is working as per requirement.

## Details
Issue | Screenshot
Incorrect group created in PROD and QA | #VALUE!